# Minutes of Meeting

AntifragiCity | WP5 4th Bi-Weekly Meeting

Date: 			22 April 2026
Work Package: 	WP5 – The Simulator for Urban Mobility Antifragility
Meeting type: 	Bi-weekly coordination meeting

# Purpose of the meeting

The meeting focused on reviewing WP5 progress, discussing and validating the circulated “WP5 – Rhoé’s Internal Understanding” document, refining the working understanding of SUMA’s role and interfaces, and clarifying practical responsibilities across WP4, WP5, and WP6, especially in relation to zone definition, pilot adaptation, and next implementation steps.

# Current WP5 status

WP5 remains in the specification and alignment phase, with T5.1 – Core SUMA API specification as the main active task. The meeting reiterated that the coming months are important for converging on a workable architecture, with August (M16) identified as a critical milestone month due to the expected delivery of D5.1, D5.4, and the related milestone.

# Progress reported

Rhoé reported the following progress under T5.1:

- consolidation of the discussions held in the previous meeting into the document “WP5 – Rhoé’s Internal Understanding”, which was circulated to the relevant partners,

- further development of the SAS (SUMO Accident Simulator) as an early proof of concept, including visualisation improvements and more network-agnostic behaviour,

- preparation for reviewing additional WP4 inputs, especially D4.2 and the related repository.

# Next steps agreed for T5.1

The following immediate next steps were identified:

- review WP4 D4.2 and the associated repository in relation to T5.1,

- continue the process for receiving and analysing the technical documentation from CU  for CUSP, subject to NDA handling,

- hold a workshop with ETH on the data-driven antifragile traffic control tool and WP4 platform outputs,

- continue discussing the WP4 system description and expected WP5 handover structure,

- finalise the implementation roadmap by the end of April,

- continue reviewing and resolving the open questions raised in the circulated SUMA/internal-understanding document.

# CUSP legal / NDA update

The NDA discussion advanced during this meeting. It was clarified that the relevant technology is licensed to Optimize AI, and the NDA shared is short and contains some negotiable items. It was also agreed that interested partners should preferably sign the same NDA document, rather than creating separate agreements. Ali committed to circulate the NDA to those who requested it.

# Main discussions

## Clarification of WP4 and WP5 scope

A substantial part of the meeting was spent discussing the circulated WP5 internal understanding document. The discussion generally confirmed the central working assumption already outlined there:

- WP4 develops the generic methods, algorithms, control logic, and KPI extraction mechanisms,

- WP5 integrates these outputs into SUMA, adapts them to pilot-specific conditions, and exposes them through a more structured and usable API/system environment,

- WP6 is expected to provide pilot-specific definitions, data, and deployment context for demonstrations.

This confirms the earlier distinction that WP5 is not expected to create entirely new control methods, but rather to make the WP4 methods usable in the pilot and demonstration context through integration, parameterisation, and workflow design.

## Discussion on inputs, outputs, and usability

The discussion refined the understanding of SUMA as a system that should:

- accept disruption events, pilot-specific data, and mobility triage inputs,

- use simulation tools such as SUMO together with WP4 methods,

- produce mobility, resilience, antifragility, and environmental indicators,

- support both technical and non-technical users through different layers of parameterisation.

It was specifically noted that SUMA should likely include a simplified or “dummy” user-facing mode for less technical stakeholders, while preserving deeper configurability in the backend.

## Protected zones / congestion zones

A major point of discussion concerned the definition of protected zones / congestion zones, especially in the context of WP4 perimeter-control methods.

The shared direction from the discussion was:

- WP4 should provide the high-level method / algorithmic logic,

- WP5 should make this usable within SUMA by supporting configuration and user interaction,

- WP6 / pilot partners should ultimately provide the pilot-specific definitions and deployment choices.

It was also acknowledged that this flexibility has limits. ETH explained that changing congestion-zone boundaries is technically possible, but because the current method is learning-based, changing the zone can require retraining, making frequent redefinition impractical. The preference therefore is for a relatively stable zone definition over a multi-year horizon, ideally informed by local authority knowledge and city-specific understanding.

## Boundary definition and KPI implications

The meeting also highlighted that precise boundary definitions are important not only for control logic, but also for KPI consistency and equilibrium modelling. It was stressed that the relevant parameters and assumptions used to define these boundaries should be identifiable and documented so that reporting and interpretation remain consistent.

## Bottom-up vs top-down scenario generation

Another useful discussion point concerned whether SUMA should support only a bottom-up event-driven workflow or also a more top-down scenario-generation mode. This directly connects to one of the open questions already raised in the internal understanding document.

The emerging conclusion was that both approaches are useful:

- bottom-up for real or historically grounded disruptions and events,

- top-down for intentionally stress-testing the system through exploratory scenarios.

This does not fully close the issue at specification level, but it does indicate that SUMA should likely support both perspectives in some form.

## Mini-GA

The group also agreed to move toward a Mini-GA / prototype-oriented exercise to translate the current conceptual understanding into a proof-of-concept path, initial API ideas, and an early data ontology direction. Yacine committed to draft and circulate an agenda for this in the coming days.

## SUMO Accident Simulator demonstration

Konstandinos also presented the current version of the SUMO Accident Simulator as a proof of concept. The demo illustrated OD-based traffic generation, simulated accidents, and the observable effect of incidents on network speed. It was presented as an early demonstrator rather than a validated result, but useful as an indication of implementation direction.

# Decisions / conclusions

The following conclusions can be considered agreed:

- the circulated WP5 internal understanding document broadly reflects the current consortium understanding and serves as a useful basis for continuing T5.1 discussions,

- WP4 provides generic methods and building blocks, while WP5 is responsible for integration, pilot adaptation, and structured/API-driven operationalisation inside SUMA,

- pilot-specific definitions such as concrete zone boundaries will need input from WP6 / city-side deployment context,

- SUMA should support both technical configurability and simpler user-facing interaction modes,

- both bottom-up and top-down scenario perspectives are relevant and should inform the T5.1 specification,

- the Mini-GA / prototype discussion should be used to move from conceptual alignment toward a more concrete implementation path.

# Action points

###### Rhoé

- Review D4.2 and the associated repository in relation to T5.1.

- Continue refining the implementation roadmap by end of April.

- Organise the workshop with ETH on data-driven antifragile traffic control.

- Continue reviewing Hichem’s repository and explore early pilot-oriented simulation tests.

- Respond to Ali’s open CUSP-related questions by email if not resolved in meeting.

###### CU / Optimize AI

- [Ali] Share the NDA with interested partners.

- Progress the NDA process so technical documentation for CUSP can be shared.

- Clarify data input/output expectations and related access conditions.

- [Yacine] Draft and circulate the agenda for the proposed Mini-GA sprint.

###### ETH

- Continue clarifying the expected form of WP4 outputs and how perimeter-control / antifragile control methods should be handed over for SUMA integration.

- Support the upcoming technical alignment discussion/workshop.

###### Pilot / city partners

- Provide administrative, study-area, and pilot-specific files/definitions where needed to support realistic adaptation and simulation work.

# Overall takeaway

This meeting moved WP5 one step further from high-level scope clarification toward a more operational shared understanding. Compared with the previous meeting, the discussion was less about whether WP4 and WP5 are distinct and more about how SUMA should make WP4 methods usable in practice: through structured integration, parameterisation, pilot-specific configuration, and an interface design that balances flexibility with usability. The remaining open questions now appear more implementation-oriented than conceptual.